{"text_format":"3","workbook":"xls","n_sheets":1,"sheets":["内资项目报批筹建总流程图"],"not_rendered":{"external_links":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"内资项目报批筹建总流程图","index":0,"n_rows":34,"n_cols":8,"rows_kept":34,"merged":[[0,2,0,7],[2,2,2,5],[6,5,7,5],[6,7,7,7],[11,7,12,7],[15,7,16,7],[27,4,29,6]],"flags":["formulas_cached_only"]}
[null,null,"The process of the setup and establishment of a domestic-funded project"]
[]
["Receiving code certificate of legal person (the local bureau of quality and technical supervision)",null,"the investor should confirm the investment plan and sign the investment agreement"]
["Open bank account (bank)"]
["Foreign Exchange Registration (Administration of Exchange Control)",null,"the company registers and gets the licence ( Nantong Administration for Industry and Commerce)",null,null,"The preparation work of the land use right of appropriated land-Investment Service Center plays a leading role (Economic Development Bureau, planning, environmental protection, head office, the land)    ",null,"Preparation for the unappropriated land to be appropriated-Invsetment Service Center plays a leading role (Economic Development Bureau,planning,head office,the land)"]
["National tax and local tax registration ( Tax Bureau)"]
["financial registration (Bureau of Finance)",null,"Project Application (Qualified institutions)",null,null,"Announcement of the land use right to the public (the municipal land and resources bureau) Announcement for 20 days, 10 workday",null,"Sign the land contract (the municipal land and resources bureau)"]
["Statistics registration (Economic Development Bureau)",null,"Energy-saving assessment document (Qualified institutions) and its approval (Economic Development Bureau)         "]
["Customs registration (Customs)  "]
["Quality registration (General Administration of Quality Supervision, Inspection and Quarantine of the People's Republic of China\n",null,"Project record-keeping (Economic and Information Commission)"]
[null,null,"Environmental assessment document (Qualified institutions) and its approval (Environmental Protection Bureau)"]
[null,null,"Safety assessment document(Qualified institutions) and its approval (Administration of Work Safety) note;the Administration of Work Safety should provide preliminary advise regarding to chemical equipment before putting on record  ",null,null,"Examination of floor plan(Planning Bureau)                                               ",null,"Construction Site Planning Permit (Planning Bureau)"]
[]
[{"$nulls":5},"Preliminary design and examination (organized by the Economic Development Bureau) Note: Occupational hygiene evaluation（Administration of Work Safety） and lighting disaster assessment(the municiapl Meteorological Bureau) are needed based on the projects"]
[]
[{"$nulls":5},"Construction drawing design(designed by qualified institutions)",null,"Land certificat(the municipal Land and Resources Bureau) Note:land fees and deed tax should be paid "]
[]
[{"$nulls":5},"Examination of construction drwing design(Office of checking designs) Note:Examination of lighting protection device, quake-proof and firefighting designs should be completed"]
[]
[{"$nulls":5},"Construction project planning permit (Planning Bureau)"]
[]
[{"$nulls":5},"Applying for quality supervision,putting invitation of tender and bidding on record, and supervision of construction safety (Construction Bureau)"]
[]
[{"$nulls":5},"Construction project planning permit (Construction Bureau)"]
[]
[{"$nulls":5},"Project engineering and installing equipment"]
[]
[{"$nulls":4},"Examination of and check on energy-saving buildings,quality of the project,planning, firefighting,environmental protection,public security,labor safety(hygiene and disease control),special equipment,planting(Public Utilities of Construction Bureau),documents(Archives Department of the Economic and Technological Development Zone), urban drainage license(Public Utilities of Construction Bureau)"]
[]
[]
[]
[{"$nulls":5},"Documentation of project completion (Construction Bureau)"]
[]
[{"$nulls":5},"Project put into operation"]